Underskiddaw Parish Council Clerks Report

Clerk’s Report to the meeting held on Tuesday 9th May 2017

Correspondence received since last meeting:

- LDNPP News Bulletin

- CALC April Newsletter

- Letter from NALC Chair

- Notification of HIMS (Highways Information management system) Information.

- Dr G Davies- March update

- Keswick Railway Footpath- Update

- Purdah Guidance for General Election (8th June 2017)

Actions on Clerk from previous meeting:

2017/13	Upload minutes to website- Done

2017/15	Chase C Saunders re commitment to longer that 6 year restoration repair period after pipeline- On-going- Action with UU

2017/15	Chase C/llr Bowness re repairs to Millbeck bridge in light of UU works-On-going still no date from CCC re these works

2017/15	Chase UU for feedback re works and Millbeck bridge closure by 14th April if not received-On-going- Action with UU

2017/15	Chase UU for contact details for on the ground team and circulate information on noticeboard etc-On-going- Action with UU

2017/15	Set up UU web page on U/S Website-On-going- Awaiting information from UU

2017/15	Upload and circulate finalised vegetation removal plans once received-On-going- Action with UU

2017/15	Chase up month by month timescale for works and share on noticeboards-On-going- Action with UU

2017/15	Chase up UU for feedback from meetings with tenants/landowners-On-going- Action with UU

2017/15	Share Haulage plans when received-On-going Action with UU

2017/15	Invite UU to July Parish Council meeting-Ongoing

2017/16	Look into process for TPOS & cost for May meeting-Information to be provided at Annual Parish Meeting in May

2017/17	Share Highways problem reporting link to all-Done

2017/18	Continue work on installation and payment of defib unit-Unit being installed in Mid May- Agreements and donation being signed at 9th May meeting

2017/18	Speak to Community Heart Beat Trust/Keswick First Responders re training-Lauren attending 9th May Annual Parish Meeting

2017/18	Speak to LDNPA re no business from Keswick Garden Centre Site-Done- Update to be provided at meeting

2017/18	Confirm resolution to KTC & ABC re Parish Boundary movement – Done but different form of words required so on May agenda

2017/18	Draft letter to go to ALL properties in U/s Share with J Wilson & J Boniface before printing- Done- Good response received

2017/19	Pay accounts-Done

2017/19	Complete internal audit- Done

2017/19	Convey decision to Cumbria dyslexia project- Done

2017/20	Submit respond to Underscar Tree Consultation- Done response awaited

2017/23	Add Clerks over time to May agenda for UU works (inc a bill)- Done

2017/23	Add reimbursement for grill costs to agenda- Tony to provide a receipt.-Done

Becx Carter

Clerk to Underskiddaw Parish Council

07786678283

underskiddawparishcouncil@hotmail.com